## Slide 1
September 21, 2026
2026
Valparaiso, Indiana / September 21, 2026
From Ground to Cloud: Our SaaS Success Story
Dave Bresson – Database Administrator
Mike Ebner – Application Programmer
Eric Hermann – Application Programmer

## Slide 2: Why SaaS?
Security
Reliability
Insurance $

## Slide 3: Length of Project
Began in August 2022
Went Live in November 2024
A little over two years (including Experience implementation)

## Slide 4: Project Kickoff
Need College Buy-In

## Slide 5: LDAP/Authentication Planning/Setup
Kish uses Active Directory/Azure/Whatever-it’s-called-these-days

## Slide 6: Data Cleanup
Get comfortable running CDSU
Only ASCII Chars 8, 10, 13, and 240 need to be removed, rest are ok to migrate

## Slide 7: Back To Base Planning
Systems Analysis meetings with each area/module
Developed Report Inventory of custom reports and screens

## Slide 8: Custom Integrations
Developed list of custom integrations in use at Kish
After training, started building out custom integrations in DataConnect – work lasted from August 2023 to Summer 2024

## Slide 9: Ellucian Experience goes Live
Getting off of Portal was really the first part of our migration to SaaS

## Slide 10: First Migration
We did our Dev environment migration in November 2023 after much planning, scanning and cleaning of data

## Slide 11: Building out reports in Insights
With data in the cloud, we could start building out reports in Insights
First we had to determine which Insights reports to do first and in what order
Work really began on Insights reports Summer of 2024 after DataConnect integrations mostly done

## Slide 12: Second Test Migration
We performed another migration to test the cleanliness of the data and simulate the Prod migration as much as possible
Find any last minute problems with data migration

## Slide 13: Migration Delayed from September to November 2024
Due to Nelnet Integration not being done, delayed project two months
Gave us time to do more Insights reports and finish up any integrations, and more Back To Base

## Slide 14: November 2024 – Go Live!
Migration to SaaS Production Friday - 11/15/2024
Employees let in for limited testing the following Tuesday – 11/19/2024
All employees let in on Wednesday - 11/20/2024

## Slide 15: Questions?

## Slide 16: Thank you!
Dave Bresson – dbresson@kish.edu
Mike Ebner – mebner@kish.edu
Eric Hermann – ehermann@kish.edu