## Slide 1
Crawl, Walk, Run: A Phased Approach to CRM Recruit Implementation
Mike Planeta & Jake Barber

## Slide 2
About us
Mike Planeta:
Manager, Student Development Technology and Training
Has worked at JJC for 10 years, in Higher Ed for 35 years.
Internal Project Manager
Jake Barber:
Manager, Admissions Technical Operations
Has worked at JJC for 7.5 years, in Higher Ed for ~13 years.
Phase 1 lead/System Administrator

## Slide 3
Why a Phased Approach?
  Limited resources​
  competing priorities​
  risk reduction​
  faster value realization​

## Slide 4
Project Governance & Buy-In
  Executive sponsor​
  steering committee​
  stakeholder engagement​
  decision framework​

## Slide 5
Defining the Phases
  Implementation (Crawl): Foundation
    Phase 1: Applications and Critical functionality
    Phase 2: Recruiting, Event Management, & Communications
  Year 1 Post Implementation (Walk): Optimization
    Common Application
    Adult Ed Application
    Selective Admissions Applications
  Year 2 onwards (Run):Automation & Scale

## Slide 6
Implementation: Crawl
Phase 1
Application management​
basic communications​
core workflows​
quick wins​
We estimated Time to completion from formal kick off would be 4-5 months
Informal work began in January
Formal Kick off held at the end of February
Went Live June 24th, 2026

## Slide 7
Data Integration & Testing
Phase 1
  Colleague on prem integration
  Data Mapping
  Refinement of existing Application Questions
  Utilizing conditional logic to combine various application forms into one
    General Admissions, Early Entry, Non-Degree/Guest Student, & International

## Slide 8
Training & Change Management
Phase 1
  Role-based training
  Documentation
  Monthly project status updates
  Regular conversations with downstream departments

## Slide 9
Implementation: Crawl
Phase 2
Expanded communication plans​
Recruitment workflows​
Event Management​
We estimated Time to completion from formal kick off would be 1-2 months
Informal work began in July
Formal Kick off held in early August
Go Live September 10th, 2026

## Slide 10
Data Integration & Testing
Phase 2
  Eliminated all recruiting integrations legacy system depended on
  Minimal Data Mapping
  Refinement of existing recruitment activities and communications

## Slide 11
Training & Change Management
Phase 2
  Role-based training
  Documentation
  Inclusion of departments with significant recruitment activity in implementation meetings

## Slide 12
Year 1 Post Implementation (Walk): Optimization
Current State
Common Application
    State of Illinois Initiative
    Formally Began Work in August
    Must Go Live by February 1st, 2027
Adult Ed Application
Selective Admissions Applications
Reporting & Dashboards
Expanded Communication Plans
Connect to Colleague SaaS

## Slide 13
Year 2 onwards (Run): Automation & Scale
Future State
Advanced automation​
Continuous improvement​
Yearly review and plan

## Slide 14
Measuring Success
Adoption​
processing time​
communication engagement​
enrollment metrics​

## Slide 15
What We Would Do Differently
Broader Training

## Slide 16
Key Takeaways & Q&A
  Start small
  Build momentum
  Demonstrate value
  Scale intentionally

## Slide 17
Thank You