## Slide 1
Leading and Implementing Change: A Six-Month Colleague Go Live
Explore the preparation, project organization, change management, and continued enhancement planning that went into a successful implementation.
Jake Stiles, Business Analyst ​
Hannah Kannal, Assistant Director of Business Solutions​
Carroll University, Waukesha, WI

## Slide 2
1 | Preparation
2 | Organization
3 | Change Management
4 | Continued Enhancements
5 | Lessons Learned
AGENDA

## Slide 3
About Carroll University
Waukesha, WI
1
Enrollment
3,176 Student Body
  2454 FT UNDG
  169 PT UNDG
  553 GRAD
2
Class Size
19.4 AVG Class Size
3
Employed Faculty
155 FT Faculty
233 PT Faculty
4
Degrees
Associates – 1
Bachelors – 4
Graduate – 12
95+ Programs

## Slide 4
How did we get here?
Ellucian Colleague demos.
August 2023
Contracts with Ellucian signed.
Sept 2023
Discovery engagements began.
Oct 2023
Configuration engagements began.
Dec 2023

## Slide 5
Go Live
Go Live
- Core and Financial Aid
April 2024
Go Live
- Student, Accounts Receivable, TouchNet, and Self-Service Platform
May 2024
Go Live
- Finance
July 2024
Go Live
- Retention Alert, ILP, eTranscripts, Insights, and Budget Management
Summer 2024

## Slide 6
Products Implemented
Colleague Key Modules​ | Colleague Supplementary Modules/Products ​ | Integrated Solutions​
Core Module​ Financial Aid Module​ Student Module​ Accounts Receivable Module​ Finance Module​ Budget Management Module​ Self-Service Module​ | Retention Alert​ Ethos​ Data Access​ Insights Reporting​ eTranscripts ​ Experience​ ILP​ | TouchNet​ SoftDocs​ Maxient​ StarRez​ Kronos​ Medicat​ Symplicity ​ EMS​
April – July 2024 Go Live​ | March – August 2024 Go Live​ | May 2024 – October 2024 Go Live​

## Slide 7
Preparation
Team, Priorities, Data, and Management

## Slide 8
CORE
Project Manager
Team Lead
OIT Support Team
Application Specialist
3 Developers
CORE - BA
Full Time Business Analyst
Part Time Business Analyst
End Users
2-3 Dedicated Staff
Project Team

## Slide 9
Key Preparation Considerations
Student Impact
Focused on least interruption for faculty and students.
Decisions influenced key areas: registration, billing, and financial aid awards.
Priorities
Identified essential imports, integrations, and modules for “go live”.
Deferred non-critical components for post-launch phases.
Clean Data
Core team members with in-depth knowledge of previous SIS data were essential.
Ensured accurate and efficient data migration.
End User Readiness
Assessed end-user ability: turnover, technical expertise, and workload.
Allocated extra time and resources for departments requiring additional support and training.

## Slide 10
Key Elements for Success
Knowledgeable Core Team
Experienced Business Analysts (25+ yeas in Registrar Office).
Deep knowledge of catalog, policy, and academic structure enabled quick module configuration.
Dedicated Imports Team
Specialized Business Analyst & Developer.
Streamlined data import process.
Change Management
Flexibility to adapt mid-project.
Embraced deviations from initial plans.
Budget Management
Budget managed by two individuals with one key decision-maker.
Simplified approval process for additional engagements, modules, and expenses.

## Slide 11
Organization
Scheduling, Access, and Projects Documents

## Slide 12
Key Organization Considerations
Scheduling
Assigned specific individuals to liaise with the Ellucian PM and consultants.
Ensured decisions on scheduling are made efficiently.
Divide and Conquer
Assigned core team staff to specific groups to ensure meeting representation.
Access
Created a shared repository for documentation, training videos, and project calendars.
Facilitated easy access and collaboration.
Escalation
Assigned a core team member to regularly attend University senior leadership meetings.
Provided updates and escalated critical matters as needed.

## Slide 13
Key Elements for Success
Regular Meetings
Developed a regular schedule of internal touch base calls outside of Colleague engagements.
Provided a space to work through issues, questions, and configuration “homework”.
Ellucian Project Site
Core team handled task updates and document uploads.
Saved time by reducing the need for extensive user training and inquiries.
Action Line
Designated three individuals to manage ticket submissions, tracking, and communication.
Ensure efficiency and accountability in ticket handling.
Tracking Systems
Developed comprehensive tracking systems.
Streamlined accountability across all areas and enhanced team alignment.

## Slide 14
Schedule Planning

## Slide 15
Import Planning

## Slide 16
Integrations Planning

## Slide 17
LIVE SIM Planning

## Slide 18
Go Live Planning

## Slide 19
Change Management
Communication, Training, Implementation, and Support

## Slide 20
Key Change Management Considerations
Communication
Highlighted key timelines and milestones via different mediums.
Tailored communication to campus groups.
Training
Developed comprehensive guides and quick reference sheets for ease of use.
Tailored topics to address key process workflows and responsibilities.
Implementation
Designed and executed an intensive live simulation testing plan beyond Ellucian’s recommendations.
Proactively shared and collaborated on go-live planning with stakeholders.
Support
Formed a specialized team to provide system troubleshooting and support.
Regularly met with end users to discuss current and potential system or process issues.

## Slide 21
Key Elements for Success
Communication
Utilized AI to streamline communication creation, saving time and resources.
Established open, consistent communication with campus stakeholders.
Training
Centralized resources on the internal portal for quick and convenient access.
Integrated Colleague training documents to maximize efficiency and consistency.
Implementation
Focused on the entire student lifecycle, ensuring all processes and interactions across offices were covered.
Incorporated key dates for all offices to align efforts and minimize disruption.
Support
Identified and addressed concerns early to minimize impact on students and staff.
Created a knowledge base for troubleshooting.

## Slide 22
Continued Enhancements
2 Years Post Go Live

## Slide 23
Key Elements
Collaborative Touchpoints
Continue regular check-ins with stakeholders.
Accounts Receivable – quarterly, Financial Aid – Biweekly, Registrar – Weekly, others as needed.
Customizations and Improvements
During rapid deployments, leveraging out-of-the-box functionality was essential.
Leverage more APIs to improve system connectivity.
Product Enhancements
Regularly check the Customer Center for upgrades and product improvements.
Work with Ellucian to identify potential new add-ons. (e.g. Smart Plan)
Requests Pipeline
Developed an internal pipeline for customization, configuration, process review, reporting, and forms requests.

## Slide 24
Key Elements
Automation
Identify processes that can be improved through automation.
Streamlined workflows to enhance efficiency and reduce manual effort.
Reporting
Reporting has been a key area of improvement since go-live.
Continue refining data analytics and reporting functionalities.
Action Line
Established a dedicated team to handle action line tickets.
Ensure continuous follow-up and efficient issue resolution.
Training
Intensive training was limited due to time constraints during implementation.
Completed second-stage training on advanced system features (e.g., rule writing, data fundamentals) post go-live.

## Slide 25
Lessons Learned
What We Would Do Differently

## Slide 26
Key Insights
Purchases
A better understanding of purchased modules and products would have been beneficial.
Some implementations were done without fully understanding the ‘why’.
Discovery
Ensure documentation is clear for all parties, including consultants.
University policies must be explicitly communicated to external teams.
Integration Management
Not all integrations were ready within the required timeframe.
Manual workarounds were necessary to transfer data across systems.
Adaptability
Emphasize the importance of being flexible.
Rely on team members, especially Subject Matter Experts (SMEs).

## Slide 27
Key Insights
Maintaining Engagement
Proactively intervene to guide conversations and maintain momentum.
Help manage expectations throughout the change process.
Training Approach
Self-paced videos and documentations were more beneficial than in-person training.
Implementing test groups for feedback would have been valuable.
Documentation Challenges
Keeping documentation updated was difficult with the accelerated timeline.
Addressed gaps to ensure processes are documented and accessible.
Data Migration
Data validation will always take longer than expected.
Manual work was required for data cleanup after imports – aim for 80% accuracy.

## Slide 28
Jake Stiles | jstiles@carrollu.edu
Hannah Kannal | hkannal@carrollu.edu ​
v